## Skills Matrix
Skills Matrix
Tasks | business analysis | process design | procurement | system specs | software customization / configuration | install devices | documentation | training
business process analysis | x
design processes |  | x
system specification |  |  |  | x
vendor contract |  |  | x
implement system |  |  |  |  | x | x
documentation | [6 empty] | x
training | [7 empty] | x
People needed | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 1
Monthly rate | 25000 | 25000 | 12000 | 20000 | 25000 | 20000 | 16000 | 16000
Estimated months | 1.5 | 2.5 | 1 | 2 | 3 | 0.5 | 2 | 2.5
Estimated cost | 75000 | 125000 | 12000 | 80000 | 150000 | 20000 | 64000 | 40000
Total Labor Costs | 566000