## Sheet1
Project | Scheduling system project
last updated
|  |  | Rank from 1 lowest to 5 highest | Rank from 1 lowest to 5 highest
Risk ID | Description | Trigger | Probability | Impact | Score | Owner | Response | Response Strategy | Expected Results | Status | Notes
1 | None of the vendor systems can provide some of the critical functionality required in the timeframe and budget required |  | 3 | 5 | 15 |  | mitigate risk | Two possibilities: 1. prioritize the functionality and select the system with the greatest functional coverage; 2. investigate the cost of customizing a system and re-evaluate the business case for those functions
2 | Systems aren’t compatible with hospital equipment, causing some functionality to be lost |  | 5 | 5 | 25 |  | mitigate risk | Reserve funding to write an interface from the required system to the existing hospital equipmen,t or replace the minimum amount of hospital equipment needed to work with the system
2a | Systems aren’t compatible with hospital equipment, causing errors in patient care data |  | 2 | 5 | 10 |  | mitigate risk | Schedule and perform extensive testing of new systems using patient data as early as possible |  |  | This is an example of one risk with different outcomes, and therefore multiple risks should be documented, with differing response strategies.
3 | Vendor scheduling delays push expenditures past the grant expiration date |  | 3 | 5 | 15 |  | transfer | Include late delivery penalties in vendor contract
4 | Key resource is pulled onto a different project, causing a delay in project completion |  | 1 | 3 | 3 |  | accept consequences |  |  |  | Note: There is no response strategy as this risk's score is less than 9.
5 | Stakeholders disagree on required functionality, which delays project implementation |  | 4 | 4 | 16 |  | mitigate risk | Obtain sponsor's commitment to resolving disagreements in scheduled status meetings held twice a month to reduce schedule impacts
6 | Appropriate levels of staff aren’t made available for training sessions |  | 2 | 3 | 6 |  | accept consequences
7 | Hospital emergency pulls resources away from project, causing schedule delays |  | 3 | 3 | 9 |  | mitigate risk | Contingency time
8 | Staff shortages alter the ability to schedule facilities to meet targets |  | 3 | 4 | 12 |  | avoid risk | Train project staff to schedule facilities, so they can perform scheduling to assist operational staff during staff shortages.
9 | Government grant managers change, altering requirements the hospital must accommodate |  | 2 | 3 | 6 |  | mitigate risk | Before funding is committed, negotiate which conditions for meeting grant requirements are not to change during the duration of the grant.
10 | Health insurance policies change and alter the nature of the patients who expect care from the hospital |  | 3 | 3 | 9 |  | accept consequences | Modify objectives to address health insurance changes and calculate impacts to the budget and schedule of the project |  |  | Although the response is set to accept consequences, it's appropriate to calculate the impact of changes to the healthcare environment. If necessary, the project objectives can be modified.
11 | Facility design causes issues with specific rooms in the hospital |  | 3 | 4 | 12 |  | mitigate risk | Allocate contingency funding to modify room configuration
12 | Facility design causes issues with specific pieces of diagnostic equipment |  | 3 | 4 | 12 |  | mitigate risk | Allocate contingency funding to test and purchase alternative equipment